## Slide 1: Michigan Shared Print Initiative (MI-SPI) Membership Meeting
Thursday, 13 September 2018
9:30 am – 2:30 pm

## Slide 2: Michigan Shared Print Initiative (MI-SPI) Membership Meeting Agenda
9:30 – 9:40 Welcome and Call to order Randy Dykhuis
9:40 – 9:50 Review agenda Helen Levenson
9:50 – 10:15 Review and current status of MI-SPI Pamela Grudzien
10:15 – 11:15 A new Collective Collection
10:15 – 10:40 Enlarging the membership Helen and Randy
10:40 – 10:50 Break
10:50 – 11:15 Timeline for MI-SPI 2.0 Pamela Grudzien
11: 15 – noon Governance structure & Memorandum of Understanding
ACTION: Set up MOU Task Force to finalize a recommended revision
Noon – 1:00 Lunch

## Slide 3: MI-SPI Membership Meeting Agenda (cont’d)
1:00 – 2:00 Issues to address and task forces to set up Pamela Grudzien
1:00 – 1:20 Validation
1:20 – 1:40 Retention commitment statements
      In MeLCAT
      ALMA community
      OCLC
1:40 – 2:00 Resource Sharing
2:00 – 2:30 Review next steps Helen and Pamela
2:30 Adjourn Randy Dykhuis

## Slide 4: Timeline for MI-SPI 2.0 Collective Collection
13 September 2018 MI-SPI Membership Meeting
1 November 2018 Committed Interest notification due to MCLS
1 December 2018 Estimated sizes of monograph collections to be contributed due to SCS
1 February 2019 SCS pricing due to MCLS
15 February 2019 MCLS distributes estimated costs to MI-SPI committed interest libraries
1 March 2019 Commitment to participate (MOU) distributed to members
1 April 2019 Deadline for all MI-SPI MOUs to be signed and on file at MCLS
15 April 2019 Library Data and Cataloging questionnaires distributed to members
15 May 2019 Deadline for Library Data and Cataloging questionnaires submitted to SCS
June – Aug. 2019 MI-SPI members extract collection data and send to SCS
15 Sept. 2019 Deadline for all MI-SPI members’ collection data files to be submitted to SCS
Sept – Dec. 2019 SCS compiles MI-SPI members’ files
Jan. – Feb. 2020 SCS analysis completed; retention assignments completed and shared with MI-SPI members

## Slide 5: Proposal for MI-SPI Governance Structure
Governing Board
  Steering Committee
    Standing Task Forces
      Collection data and analysis
      Resource Sharing and metadata

## Slide 6: Thank you for attending!
Meeting adjourned